## Sheet1
ID | Risk Description | Impact (H/M/L) | Probability (H/M/L) | Mitigation | Owner | Status
R1 | Data quality defects | High | Medium | Early profiling and cleansing; allocate owners | Data Lead | Open
R2 | Custom interface failure | High | Low | Parallel testing; contingency interface plan | Integration Lead | Open
R3 | Resource availability | Medium | Medium | Plan resource backup; vendor support | Program Manager | Open