## Sheet1
Step # | Activity | Owner | Start (T-x) | End (T-x) | Dependency | Status | Notes
1 | Announce freeze window | Program Manager | T-7 | T-7 | N/A | Planned | Communicate widely
2 | Final EBS extract | Data Team | T-3 | T-3 | Step 1 | Planned | Ensure backups
3 | SAP master load & validation | Data Team | T-2 | T-1 | Step 2 | Planned | Validate masters before transactions
4 | Load open transactions & reconcile | Business Owner | T | T | Step 3 | Planned | Reconcile counts & totals
5 | Open SAP for users | Program Manager | T | T | Step 4 | Planned | Announce completion